## Product-Backlog
COMPLAINT MANAGEMENT SYSTEM - PRODUCT BACKLOG
Tech Stack: ASP.NET Core Web API ¦ Angular/React/MVC ¦ SQL Server ¦ Docker ¦ Kubernetes ¦ Azure CI/CD
Architecture: Client (Angular/React/MVC) -> ASP.NET Core Web API -> SQL Server ¦ Docker -> K8s -> Azure DevOps CI/CD -> MS Azure
ID | AS A... | I WANT TO... | SO THAT... | PRIORITY | STORY POINTS | SPRINT | STATUS | STATUS | PRIORITY
101 | As a citizen | I want to register and log in to the portal | so that I can submit and track my complaints online | High | 8 | 1 | To Do | To-Do | High
102 | As a citizen | I want to submit a complaint with category, description and attachments | so that relevant authorities receive complete information | High | 8 | 1 | To Do | In-Progress | Medium
103 | As a citizen | I want to view real-time status of my complaint | so that I know the progress without calling anyone | High | 5 | 2 | To Do | Complete | Low
104 | As a citizen | I want to receive email/SMS notifications on status changes | so that I am informed at every stage automatically | Medium | 5 | 2 | To Do | Overdue
105 | As a citizen | I want to view my complaint history | so that I can reference previous issues I raised | Medium | 5 | 3 | To Do | On Hold
106 | As an admin | I want to view all incoming complaints on a dashboard | so that I can quickly assess workload and priorities | High | 8 | 3 | To Do
107 | As an admin | I want to assign complaints to appropriate department/officer | so that each complaint is handled by the right team | High | 5 | 4 | To Do
108 | As an admin | I want to update complaint status and add internal notes | so that citizens and officers are kept informed | High | 5 | 4 | To Do
109 | As an admin | I want to set priority and escalation rules for complaints | so that critical issues are resolved faster | Medium | 5 | 5 | To Do
110 | As a dept officer | I want to view complaints assigned to me | so that I can manage my workload efficiently | High | 5 | 5 | To Do
111 | As a dept officer | I want to add resolution notes and close a complaint | so that the system records outcomes accurately | High | 5 | 6 | To Do
112 | As a dept officer | I want to request additional info from the citizen | so that I can resolve complaint with complete data | Medium | 3 | 6 | To Do
113 | As an admin | I want to generate reports on volume, resolution time and SLA breaches | so that management can analyse performance | Medium | 8 | 7 | To Do
114 | As an admin | I want to configure SLA rules per complaint category | so that resolution deadlines are enforced automatically | Low | 5 | 7 | To Do
TOTAL BACKLOG ITEMS | [6 empty] | 14

## Sprint-Backlog
COMPLAINT MANAGEMENT SYSTEM - AGILE SPRINT BACKLOG (7 SPRINTS) WITH BURNDOWN CHART
BACKLOG TASK & ID | ASSIGNED TO | STATUS | ORIG. ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
SPRINT 1 ¦ Sprint 1 - Authentication and Complaint Submission
User Story 101 - Citizen Registration and Login
Design registration and login UI (Angular/React/MVC) | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Implement ASP.NET Core Identity and JWT authentication | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1
Create User entity and SQL Server migrations (EF Core) | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Unit tests for auth endpoints (xUnit) | Kushagra Saxena | To-Do | 4 hrs | 1 | 1 | 1 | 1 | 0
User Story 102 - Submit Complaint
Design complaint submission form UI | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Implement Complaint POST API endpoint (Web API) | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1
File upload service - Azure Blob Storage integration | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Generate unique complaint reference number | Kushagra Saxena | To-Do | 3 hrs | 1 | 1 | 1 | 0 | 0
SPRINT 2 ¦ Sprint 2 - Status Tracking and Notifications
User Story 103 - Real-Time Status Tracking
Design citizen dashboard with status timeline UI | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Implement GET complaint status API with history | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Status history audit log table (SQL Server) | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Pagination and filter for complaint list | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
User Story 104 - Email/SMS Notifications
Integrate SendGrid (email) and Twilio (SMS) | Kushagra Saxena | To-Do | 7 hrs | 2 | 2 | 2 | 1 | 0
Build notification trigger service (.NET Background Service) | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Notification opt-in/out settings API | Kushagra Saxena | To-Do | 4 hrs | 1 | 1 | 1 | 1 | 0
Retry logic with exponential back-off | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
SPRINT 3 ¦ Sprint 3 - Complaint History and Admin Dashboard
User Story 105 - Complaint History
Design complaint history page with filters | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Implement paginated complaint history API | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Export to PDF/Excel (EPPlus/iTextSharp) | Kushagra Saxena | To-Do | 7 hrs | 2 | 2 | 1 | 1 | 1
Re-open complaint within 7 days workflow | Kushagra Saxena | To-Do | 4 hrs | 1 | 1 | 1 | 1 | 0
User Story 106 - Admin Dashboard
Design admin dashboard with Chart.js visualisations | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1
Implement dashboard summary API (counts and trends) | Kushagra Saxena | To-Do | 7 hrs | 2 | 2 | 2 | 1 | 0
SLA breach alert component and SignalR real-time refresh | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Role-based access control for admin routes | Kushagra Saxena | To-Do | 5 hrs | 1 | 1 | 1 | 1 | 1
SPRINT 4 ¦ Sprint 4 - Complaint Assignment and Status Management
User Story 107 - Assign Complaints
Department and officer management CRUD APIs | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Auto-assignment rules engine (category-based) | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1
Assignment notification email to officer | Kushagra Saxena | To-Do | 5 hrs | 2 | 2 | 1 | 0 | 0
Bulk assignment UI and API endpoint | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
User Story 108 - Update Status and Internal Notes
Status update API with role-based access | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Internal notes vs public update data model | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Status change audit log (timestamp and user) | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Citizen notification on public status update | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
SPRINT 5 ¦ Sprint 5 - Priority, Escalation and Officer Portal
User Story 109 - Priority and Escalation Rules
Priority configuration UI and CRUD API (Admin) | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Escalation timer service (.NET Background Service) | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1
Auto-reassignment on escalation trigger | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Escalation history logging table | Kushagra Saxena | To-Do | 4 hrs | 1 | 1 | 1 | 1 | 0
User Story 110 - Officer Dashboard
Design officer-specific complaint dashboard | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Assigned complaints API with priority sort (Officer role) | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Overdue complaint flagging business logic | Kushagra Saxena | To-Do | 5 hrs | 2 | 2 | 1 | 0 | 0
Accept/decline assignment with reason API | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
SPRINT 6 ¦ Sprint 6 - Resolution Workflow and Additional Info
User Story 111 - Resolve and Close Complaint
Resolution notes and attachment upload UI (Officer) | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Close complaint API with mandatory resolution note | Kushagra Saxena | To-Do | 6 hrs | 2 | 2 | 1 | 1 | 0
Closure notification email to citizen | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Citizen re-open within 7 days workflow | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
User Story 112 - Request Additional Information
Officer query message UI and POST API | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
Complaint status -> Awaiting Info transition logic | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
SLA pause/resume on Awaiting Info state (EF Core) | Kushagra Saxena | To-Do | 7 hrs | 2 | 2 | 1 | 1 | 1
Auto-escalation after configurable wait threshold | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
SPRINT 7 ¦ Sprint 7 - Reports, SLA Config and Azure Deployment
User Story 113 - Reports and Analytics
Design reports module UI with filters and charts | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1
Reports API: Volume, SLA Compliance, Resolution, Officer KPIs | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1
PDF/Excel/CSV export service (iTextSharp/EPPlus) | Kushagra Saxena | To-Do | 7 hrs | 2 | 2 | 1 | 1 | 1
Scheduled report email delivery (Hangfire) | Kushagra Saxena | To-Do | 5 hrs | 2 | 1 | 1 | 1 | 0
User Story 114 - SLA Config and DevOps Deployment
SLA rule CRUD API and admin configuration UI | Kushagra Saxena | To-Do | 6 hrs | 2 | 1 | 1 | 1 | 1
Dockerise API and frontend (Dockerfile + Docker Compose) | Kushagra Saxena | To-Do | 7 hrs | 2 | 2 | 1 | 1 | 1
Kubernetes manifests (Deployment, Service, Ingress, Secrets) | Kushagra Saxena | To-Do | 7 hrs | 2 | 2 | 1 | 1 | 1
Azure DevOps CI/CD: Build -> Test -> Docker Push -> Deploy to AKS | Kushagra Saxena | To-Do | 8 hrs | 2 | 2 | 2 | 1 | 1

## User Story
COMPLAINT MANAGEMENT SYSTEM - USER STORIES
S.NO | USER STORY | ACCEPTANCE CRITERIA
1 | As a citizen, I want to register and log in to the portal, so that I can submit and track my complaints online. | Registration form: Full Name, Email, Mobile, Password. All mandatory fields validated before submission. Email format and password strength enforced. OTP/email verification required. JWT-based authentication on login. Failed login attempts limited (brute-force protection).
2 | As a citizen, I want to submit a complaint with category, description and attachments, so that authorities receive complete information. | Form: Title, Category, Sub-category, Description, Location, Attachment. Attachment limited to 5 MB. Unique complaint reference number generated. Confirmation sent via email/SMS. Duplicate complaints prevented within 24 hours.
3 | As a citizen, I want to view real-time status of my complaint, so that I know the progress without calling anyone. | Status flow: Submitted -> Assigned -> In Progress -> Resolved -> Closed. Status history/timeline visible. Filter by date, category, status. Expected resolution date shown per SLA.
4 | As a citizen, I want to receive email/SMS notifications on status changes, so that I am informed at every stage. | Notification on every status change. Includes: Complaint ID, new status, resolution date. Opt-in/out in profile settings. Failed notifications retried and logged.
5 | As a citizen, I want to view my complaint history, so that I can reference previous issues. | Listed in reverse chronological order. Shows: Ref No., Category, Status, Submitted Date, Resolved Date. Pagination for large records. Export to PDF/Excel. Closed complaints re-openable within 7 days.
6 | As an admin, I want to view all complaints on a dashboard, so that I can assess workload and priorities. | Shows totals: Open, In Progress, Resolved, Overdue. Bar/pie charts by category. SLA breach alerts in red. Auto-refresh every 30 seconds.
7 | As an admin, I want to assign complaints to department/officer, so that the right team handles each complaint. | Select department and officer from dropdown. Auto-assignment configurable by category. Assigned officer emailed. Reassignment logs reason and timestamp. Bulk assignment supported.
8 | As an admin, I want to update complaint status and add internal notes, so that citizens and officers are kept informed. | Status changeable at any stage. Internal notes visible to admin/officers only. Public update added separately. All changes logged with timestamp. Citizen notified on public updates.
9 | As an admin, I want to set priority and escalation rules, so that critical issues are resolved faster. | Priority levels: Critical, High, Medium, Low. Escalation after configurable time thresholds. Auto-reassignment on escalation. Escalation history logged. Admin alerted when escalation triggers.
10 | As a dept officer, I want to view complaints assigned to me, so that I can manage my workload efficiently. | Dashboard shows assigned complaints with priority. Filter by status, date, priority. Overdue flagged prominently. Expected resolution date visible. Accept or decline assignment with reason.
11 | As a dept officer, I want to add resolution notes and close a complaint, so that outcomes are recorded. | Resolution notes mandatory before closure. Attachments uploadable as proof. Citizen notified on closure. Citizen can re-open within 7 days. Closure timestamp and officer ID logged.
12 | As a dept officer, I want to request additional info from the citizen, so that I can resolve the complaint. | Officer sends query via portal. Status changes to Awaiting Info. SLA timer paused during wait. Citizen notified. Auto-escalated if no response after threshold.
13 | As an admin, I want to generate reports on volume, resolution time and SLA breaches, so that management can analyse performance. | Report types: Volume, Resolution Time, SLA Compliance, Officer KPIs. Filterable by date, category, department, officer. Charts: bar, line, pie. Export: PDF, Excel, CSV. Scheduled delivery via email.
14 | As an admin, I want to configure SLA rules per category, so that resolution deadlines are enforced automatically. | SLA rules per category: response and resolution time. Timer starts on submission. Breach alerts before deadline. Breached complaints flagged. Changes logged with effective date.